## Instructions
INSTRUCTIONS- READ FIRST- then fill out 'Project GANTT' sheet
Number | Work packages (WP), Activity, Deliverable (D) and Milestone (M) Titles | Activity Lead | Involved Participants (Acronym from application question 1I) | Start Date | End Date | Year 1 | [11 empty] | Year 2 | [11 empty] | Year 3
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
| WP 1 Project management and coordination |  |  | DD.MM.YY | DD.MM.YY
1.1 | Project management | A1 | all | 2027-02-01 | 2029-01-31
1.2 | Dissemination and communication | A1 | all | 2027-12-01 | 2029-01-31 | bar: Year 1 11 to Year 1 12; Year 2 18; Year 3 27 to Year 3 28; Year 3 35 to Year 3 36
M1.1 | Project meetings | A1 | all | 2027-02-01 | 2029-01-31 | bar: Year 1 1; Year 1 3; Year 1 5; Year 1 7; Year 1 9; Year 1 11; Year 2 13; Year 2 15; Year 2 17; Year 2 19; Year 2 21; Year 2 23; Year 3 25; Year 3 27; Year 3 29; Year 3 31; Year 3 33; Year 3 35
M1.2 | Final conference | A1 | all |  | 2028-10-31 | bar: Year 3 33
D1.1 | Report | A1 | all | 2027-07-01 | 2027-01-31 | bar: Year 1 6; Year 1 12; Year 2 18; Year 2 24; Year 3 30; Year 3 36
WP 2 Lab experiment 1
2.1 | Selection of targets | A2 | A1, A2, C1-R1, C2-R1 | 2027-02-01 | 2027-05-30 | bar: Year 1 1 to Year 1 4
2.2 | Test of method 1 | A2-R1 | A2, A2-R1 | 2027-05-01 | 2027-08-31 | bar: Year 1 4 to Year 1 7
2.3 | Test of method 2 | A2-R2 | A2, A2-R2 | 2027-07-01 | 2027-10-31 | bar: Year 1 6 to Year 1 9
D2.1 | Data published in database | A2 | A2, A2-R1, A2-R2 |  | 2027-10-31 | bar: Year 1 9
M2.1 | Select 5 targets for in vitro platform | A2 | A1, A2, C1-R1, C2-R1 |  | 2027-05-30 | bar: Year 1 4
M2.2 | Select method to be used | A2 | A1, A2, C1-R1, C2-R1 |  | 2027-10-31 | bar: Year 1 9
WP 3 Set-up of test platform
3.1 | Set-up of test platform | A1 | A1, A1-R1 | 2027-07-01 | 2028-11-30 | bar: Year 1 6 to Year 1 10
3.2 | Test of 5 targets | A1-R1 | A1, A1-R1 | 2027-11-01 | 31.09.28 | bar: Year 1 10 to Year 2 20
M3.1 | Selection of 3 targets | A1 | A1, A2, C1-R1, C2-R1 |  | 31.09.28 | bar: Year 2 20
D3.1 | Data submitted in open-access paper | A1 | A1, A2, A1-R1, A2-R1 |  | 01.01.29 | bar: Year 2 24
WP 4
Activity 1
Activity 2
Activity 3
Deliverable/Milestone 1
Deliverable/Milestone 2
Deliverable/Milestone 3
Save and Upload to Application as PDF:
On the Project GANTT sheet: Select File - Print.
In PRINT settings:
Choose a PDF printer (e.g. Adobe, Microsoft)
Select 'Print Active Sheets'
Landscape Orientation, A4
Select 'Narrow Margins'
Fit Sheet on One Page (If you have many rows of text, it may be better to 'Fit All Columns on One Page' and print across 2 pages)
State the title of each WP. WP1 should be project management.
You can add and delete Work Packages/activities as needed.
Use abbreviations from IBIS OIS application questions.
Milestones mark important events. Schedule enough project meetings to ensure involvement of all applicants and company partners.
Deliverables can be e.g., reports, datasets and publications.
Visualize the timeline for individual activities like this.
Milestones and Deliverables might only have end-dates.
Milestones (M) and Deliverables (D) must be derived from a specific activity in the work package.
Year 1 month 1 is the first month that you start your project.
If your project does not span 36 months, delete extra month columns once your GANTT is completed.

## Project GANTT
Number | Work packages (WP), Activity, Deliverable (D) and Milestone (M) Titles | Activity Lead | Involved Participants (Acronym from application question 1I) | Start Date | End Date | Year 1 | [11 empty] | Year 2 | [11 empty] | Year 3
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
| WP 1 Project Management and Coordination |  |  | DD.MM.YY | DD.MM.YY
1.1 | Activity 1
1.2 | Activity 2
1.3 | Activity 3
Deliverable/Milestone 1
Deliverable/Milestone 2
Deliverable/Milestone 3
WP 2 name
2.1 | Activity 1
2.2 | Activity 2
2.3 | Activity 3
Deliverable/Milestone 1
Deliverable/Milestone 2
Deliverable/Milestone 3
WP 3 name
Activity 1
Activity 2
Activity 3
Deliverable/Milestone 1
Deliverable/Milestone 2
Deliverable/Milestone 3
WP 4 name
Activity 1
Activity 2
Activity 3
Deliverable/Milestone 1
Deliverable/Milestone 2
Deliverable/Milestone 3
WP 5 name
Activity 1
Activity 2
Activity 3
Deliverable/Milestone 1
Deliverable/Milestone 2
Deliverable/Milestone 3
WP 6 name
Activity 1
Activity 2
Activity 3
Deliverable/Milestone 1
Deliverable/Milestone 2
Deliverable/Milestone 3
WP 7 name
Activity 1
Activity 2
Activity 3
Deliverable/Milestone 1
Deliverable/Milestone 2
Deliverable/Milestone 3